PLOWBIRD

Partner Playbook

Your step-by-step guide to launching before the first snowfall

For: Danny (marketing, customers, hiring, financials)

Tech partner: Matt (app, website, payments setup)

Written: October 21, 2026

Launch-ready target: Friday, November 13, 2026

This is the friendly version of business/PARTNER-PLAYBOOK.md in the Plowbird GitHub repo. If the two ever disagree, the GitHub version is the one we keep up to date.

Contents

01   The big picture   What Plowbird is, who does what, the numbers

02   Decide together this week   Quick decisions to start recruiting

03   Week by week to launch   Your checklist from Oct 21 to Nov 17

04   Launch go / no-go checklist   What must be true before real orders

05   Storm-night playbook   The evening before, during, the morning after

06   After launch   Marketing, hiring and money, ongoing

07   What you need from Matt   Tech asks and when

08   Launch budget worksheet   Fill in real quotes

09   Using Claude to help   Setup and things to ask

10   Where everything lives   Files and links

# 1. The big picture

## What Plowbird is

On-demand driveway plowing in the Twin Cities. Think DoorDash, but for plow trucks. A customer opens plowbird.app, sees the price up front, orders a plow (now or scheduled), watches the truck on a live map, and pays only after the driveway is clear.

Local plow operators are the drivers. They are independent contractors with their own trucks. They keep 80% of each job plus 100% of tips, paid automatically through Stripe.

## Who does what

| Role | Danny | Matt |
| --- | --- | --- |
| Focus | Marketing, getting customers, hiring, money and paperwork | The app, the website, payments setup, technical fixes |
| Examples | Forms the business, gets insurance, recruits drivers, prints flyers, runs the books | Turns on live payments, sets the service area, adds promo codes, fixes bugs |

## The goal

Be live for real, paying orders before the first plowable snow (2 inches or more). In the Twin Cities that is usually mid-to-late November. We aim to be ready by November 13 in case snow comes early.

## The strategy in one sentence

Drivers first, then customers, in one small area. If a customer orders and nobody shows up, we lose them for good. So we sign up drivers before we advertise, and we only advertise where those drivers can reach a driveway in about 20 minutes.

The pilot area is the west metro: Plymouth, Wayzata, Hopkins and Minnetonka, so drivers stay central. We add neighbors (Medina, Orono, Long Lake, Golden Valley, St. Louis Park, Maple Grove, Eden Prairie) as drivers sign up.

Outside the pilot ZIPs, the website says "Coming soon to <city>" and collects a waitlist email. The waitlist by ZIP (in the admin dashboard) shows where to expand next.

| City | Starter ZIPs (verify before launch) |
| --- | --- |
| Plymouth | 55441, 55442, 55446, 55447 |
| Wayzata | 55391 |
| Hopkins | 55343 |
| Minnetonka | 55305, 55345 |

## The numbers to know

| Item | Amount |
| --- | --- |
| Customer price | From $35 (1-car). A 2-car driveway is $49.50. |
| Driver pay | $36 for a 2-car driveway, plus 100% of tips |
| What Plowbird keeps | About $11.75 per 2-car job, after Stripe fees |
| Launch offer | FIRSTPLOW: $10 off the first plow (new customers, one per household, through March 31, 2027) |
| Storm Pass subscription | $79 / $99 / $129 per month (1-car / 2-car / 3+ car), plows automatically every qualifying storm |

Items marked  ASK A PRO in this guide need a quick check with a lawyer, accountant or insurance broker. This guide is a plan, not legal or tax advice.

# 2. Decide together this week

Just the quick decisions you need to start recruiting and marketing. The bigger business setup (LLC, ownership, insurance) comes in Week 3, before we take real paid orders.

| Done | Step | Details |
| --- | --- | --- |
| ☐ | Final pilot ZIP codes | Start with the west-metro list in section 1. Matt sets them in the app. Add a ZIP once 2+ approved drivers live within about 15 minutes of it. |
| ☐ | Support email and phone | For the website, the flyers and Google. A Google Voice number works well. |
| ☐ | Starter budget | Enough for printing, Craigslist posts and maybe a few boosted posts. Agree who pays and keep every receipt: it becomes a business expense once the LLC exists. |
| ☐ | A short written handshake ASK A PRO | One page, signed by both: who does what, how you'll split ownership, and that the details go into the LLC agreement later. Two people working on a business together are usually treated as a partnership by default, so put it in writing now. |
| ☐ | Launch-week driver bonus? | Optional: a guaranteed hourly minimum for drivers during the first storm. Decide yes or no so recruiting can mention it. |

Why the LLC can wait (a little): posting ads, calling drivers and collecting waitlist sign-ups don't take money from customers or put anyone on a driveway. Why it can't wait past Week 3: once real plows hit real driveways, a damaged garage door or a slip-and-fall claim lands on you personally unless there's an LLC and insurance in place. Insurance can also take 1–2 weeks to bind, so start quotes in Week 2.

# 3. Week by week to launch

| Week | Dates | Focus | Goal by the end |
| --- | --- | --- | --- |
| 1 | Oct 21 – 27 | Drivers + waitlist start | Ads up, calls made, accounts open |
| 2 | Oct 28 – Nov 3 | Vet drivers, push the waitlist | 20+ applications, flyers out, insurance quotes in |
| 3 | Nov 4 – 10 | Make it official | LLC, bank, insurance, Stripe live, 10–15 approved drivers |
| 4 | Nov 11 – 17 | Get launch-ready | Go/no-go passed, test order done |

## Week 1 (Oct 21 – 27): Start drivers and the waitlist

DRIVERS

| Done | Step | Details |
| --- | --- | --- |
| ☐ | Post driver ads | Craigslist, Facebook plow groups, local buy/sell groups. The ads are in marketing/outreach/. Link to plowbird.app/apply with a tag, e.g. plowbird.app/apply?utm_source=craigslist. |
| ☐ | Call landscapers and plow companies | West-metro list: marketing/outreach/west-metro/driver-leads.csv. Script: cold-email-and-phone-script.md. Track each call in a spreadsheet. |
| ☐ | Hang driver posters | At plow dealers, farm-supply and hardware stores (marketing/print/plowbird-driver-poster.pdf). Always ask first. |

WAITLIST

| Done | Step | Details |
| --- | --- | --- |
| ☐ | Post online | Nextdoor and local Facebook groups, using customer-posts.md. Frame it as "join the waitlist for $10 off your first plow". Follow each group's rules. |
| ☐ | Book newsletters and events | Newsletters and events often close weeks ahead. Events, schools, HOAs and bulletin boards with timing are in marketing/outreach/west-metro/flyer-spots.csv. |

ACCOUNTS   Use a Plowbird email and add Matt as a second admin

| Done | Step | Details |
| --- | --- | --- |
| ☐ | Support email and phone | support@plowbird.app (forwarding is fine) and a Google Voice number. |
| ☐ | Google Business Profile | Start now: verification can take days or weeks. The copy is ready in marketing/outreach/google-business-profile.md. Set it up as a service-area business with no public address. |
| ☐ | Social and email tools | Nextdoor business page, Facebook page, Instagram, Mailchimp. Mailchimp needs a mailing address on every email (a PO box works). |

## Week 2 (Oct 28 – Nov 3): Vet drivers and push the waitlist

Goals: 20+ driver applications (so 10–15 make it through vetting, 2+ near each suburb) and the waitlist growing toward 300–500.

DRIVERS

| Done | Step | Details |
| --- | --- | --- |
| ☐ | Vet each driver | The /apply form already collects insurance answers, license state and expiry, 21+, and a signed contractor agreement. On a 10-minute call, check their license, insurance papers and a photo of the truck with the plow. Store copies in a private folder, never in GitHub. |
| ☐ | Approve drivers in the app | At plowbird.app/admin, Drivers tab. Matt needs to give you admin access first. |
| ☐ | Keep recruiting | Follow up on calls, repost ads, fill any suburb with fewer than 2 drivers. |

WAITLIST

| Done | Step | Details |
| --- | --- | --- |
| ☐ | Print flyers and cards | Files are in marketing/print/. Test-scan every QR code with an iPhone and an Android before the full print run. |
| ☐ | Hang posters | Libraries, rec centers, coffee shops, hardware stores in the pilot cities (flyer-spots.csv). Ask first. |
| ☐ | Drop coupon cards | On blocks with long driveways. Doors and porches only, never in mailboxes, and check the city's rules on door drops. |
| ☐ | Reach realtors | Offer a "first snow is on us" closing gift for new homeowners (agree on a budget first). |

START THE PAPERWORK

| Done | Step | Details |
| --- | --- | --- |
| ☐ | Get insurance quotes ASK A PRO | Use an independent commercial broker. Ask about general liability, hired and non-owned auto, an umbrella policy, and what drivers must carry (for example $1M liability and commercial auto with a plow endorsement). |
| ☐ | Book the attorney | Schedule the operating agreement and driver-terms review for Week 3. |

## Week 3 (Nov 4 – 10): Make it official

Everything here must be done before the first real paid order.

LEGAL

| Done | Step | Details |
| --- | --- | --- |
| ☐ | Form the Minnesota LLC | Online at sos.state.mn.us (Start a business). Usually same day. Check the current fee on the site. |
| ☐ | Operating agreement ASK A PRO | Turn your Week 1 handshake into the real thing with a Minnesota small-business attorney: ownership, roles, vesting, spending limits. |
| ☐ | Get an EIN (tax ID) | Free at irs.gov, about 10 minutes. Never pay a website to do this for you. |
| ☐ | Driver contractor terms ASK A PRO | Have the attorney review them. Drivers are contractors: don't set their hours or stop them from doing other plow work. |
| ☐ | Ask the accountant about sales tax ASK A PRO | Is residential snow plowing taxable in Minnesota? Are Storm Pass subscriptions treated differently? Do we need a MN tax ID? |
| ☐ | Check city rules | Ask each pilot city whether a marketplace like ours needs a business license. |

MONEY AND INSURANCE

| Done | Step | Details |
| --- | --- | --- |
| ☐ | Open a business bank account | In the LLC's name. You need the EIN and the LLC paperwork. Get a debit card for ads and printing. |
| ☐ | Set up bookkeeping | QuickBooks Online, Wave or similar. Connect the bank and Stripe. Log the receipts from Weeks 1–2. |
| ☐ | Buy the insurance | Bind the policy (a policy in hand, not a quote). Tell Matt the driver minimums so the sign-up form and ads match. |
| ☐ | Give Matt the Stripe details | Business name, EIN, address, bank account and owner info. Matt turns on live payments. |

GET READY TO SELL

| Done | Step | Details |
| --- | --- | --- |
| ☐ | Get the launch email ready | Load it into Mailchimp (marketing/print/plowbird-email.zip). Also have a "snow emergency tonight" post ready. |
| ☐ | Driver kickoff call | Walk drivers through the app and how they get paid. Make sure every driver has finished payout setup. |

## Week 4 (Nov 11 – 17): Get launch-ready

| Done | Step | Details |
| --- | --- | --- |
| ☐ | Go / no-go check | Go through section 4 with Matt. Everything must be checked. |
| ☐ | Do a real test order | Order a real, paid plow yourself in a pilot ZIP. Make sure a driver takes it, payment goes through and the driver's pay shows up. |
| ☐ | Build the storm roster | Which drivers will be online for the first storm, by suburb. Have their phone numbers. |
| ☐ | Watch the forecast | weather.gov/mpx. When 2"+ is forecast, follow the storm-night playbook (section 5). |

# 4. Launch go / no-go checklist

Both of you sign off on every line before we turn on real orders.

| Done | Check | Who |
| --- | --- | --- |
| ☐ | LLC formed, EIN issued, bank account open, operating agreement signed | Danny |
| ☐ | Insurance bought (a policy in hand, not just a quote) | Danny |
| ☐ | Stripe live payments turned on, driver payouts working | Matt, with Danny's business info |
| ☐ | Demo mode off, service area set to the pilot ZIPs | Matt |
| ☐ | Terms and Privacy reviewed by the attorney, business name and address filled in | Danny reviews, Matt updates |
| ☐ | Someone answers the support email and phone | Danny |
| ☐ | 10+ approved drivers with payouts set up, at least 2 per suburb | Danny |
| ☐ | Test order completed start to finish | Both |
| ☐ | Storm-night roster and on-call plan | Danny |

# 5. Storm-night playbook

## The evening before (when 2"+ is forecast)

- Text every approved driver: when the snow is coming, and who will be online.

- Around 7 pm, send the waitlist email and post in the neighborhood groups.

- If Minneapolis or St. Paul declares a snow emergency, post the "snow emergency tonight" version.

## During the storm

- Watch orders live at plowbird.app/admin. Every order needs a driver. Orders with no driver after 10 minutes cancel automatically and the customer isn't charged.

- If orders are waiting, call drivers directly.

- Answer support messages quickly. Write down every problem.

## The morning after

- Ask happy customers for a Google review.

- Pay any bonus you promised drivers.

- Review with Matt: how many orders, how fast drivers accepted, cancellations, complaints, what broke.

# 6. After launch: your ongoing jobs

## Marketing and customers

- Every week: open plowbird.app/admin (Dashboard). Check the waitlist by source and by ZIP, and put more money into what works.

- After every storm: ask for Google reviews within 24 hours.

- December: push Storm Pass (snowbirds, older homeowners and their grown kids).

- Referrals: "Give $10, get $10". Decide the budget, then ask Matt to build it.

## Hiring

- Drivers are contractors. Keep recruiting all season. Get 2+ per suburb before adding new ZIP codes.

- Employees (for example a storm-night dispatcher or part-time support): before the first hire you need Minnesota unemployment insurance registration, workers' comp insurance, payroll (Gusto or similar) and I-9/W-4 paperwork. Talk to the accountant first.  ASK A PRO

## Money

| How often | What to do |
| --- | --- |
| Weekly | Match Stripe payouts to the bank. Track revenue, driver pay, Stripe fees, promo cost and ad spend. |
| Monthly | Profit and loss, cash on hand, monthly spend, and what it costs to get a customer from each channel. |
| Quarterly | Estimated taxes and any sales tax filing (the accountant will tell you which). |
| January | Driver 1099 tax forms. Stripe can file and send these for us; turn it on with Matt. ASK A PRO |

# 7. What you need from Matt

Open a GitHub issue in the repo or message Matt. Please don't edit the app/ or server/ folders yourself.

| Done | Ask | When |
| --- | --- | --- |
| ☐ | Give Danny admin access (dashboard, waitlist, driver approvals) | Week 1 |
| ☐ | Set the pilot ZIP codes and the area name shown on the site | Week 1 |
| ☐ | Put the support email and phone on the Contact page | Week 1–2 |
| ☐ | Update the driver form and Terms with the insurance minimums and the business name and address | Week 3 |
| ☐ | Add partner promo codes (like WAYZATA10) before a partner publishes one | As needed |
| ☐ | Turn on Stripe live payments, driver payouts and 1099 settings | Week 3 |
| ☐ | Turn demo mode off | Launch day |

# 8. Launch budget worksheet

Fill in real quotes as you get them.

| Item | Where to get the number | Amount |
| --- | --- | --- |
| LLC filing | sos.state.mn.us |  |
| Attorney (agreement, Terms review, driver terms) | Ask for a flat-fee quote |  |
| Insurance | Broker quote |  |
| Printing (posters and card stock) | Local print shop quote |  |
| Craigslist posts | marketing/outreach/places-to-post.md |  |
| Social / Nextdoor ads (optional) | You set the cap |  |
| FIRSTPLOW discounts | $10 × expected first orders |  |
| Driver launch bonus (optional) | $ per hour × drivers × hours |  |
| Phone, mailbox, email | Small monthly costs |  |
| Bookkeeping software | Monthly plan |  |
| Total |  |  |

# 9. Using Claude to help

Claude can draft almost everything in this guide: emails, ads, call scripts, budgets, spreadsheets and checklists. You review it and do the sending, signing and paying.

## Set it up once

If you use Claude Code with the GitHub repo: nothing to do. Claude reads business/CLAUDE.md and marketing/handoff/CLAUDE.md automatically when it works in those folders.

If you use claude.ai:

- Create a Project called "Plowbird".

- Copy the contents of business/CLAUDE.md and marketing/handoff/CLAUDE.md into the Project instructions.

- Upload this guide, marketing/GAMEPLAN.md and the files in marketing/outreach/ as Project files.

## Things to ask it

- "Write a Craigslist ad for plow drivers in Plymouth, with a tracked link."

- "Make a call log spreadsheet for the businesses in driver-leads.csv."

- "Draft questions for my first meeting with an insurance broker."

- "Write the snow-emergency Nextdoor post for Wayzata for tonight."

- "Build a monthly P&L template using our unit economics."

- "Draft a GitHub issue asking Matt to add the promo code WAYZATA10."

Never paste driver licenses, insurance certificates, Social Security numbers, bank details or customer lists into the GitHub repo. Keep them in a private folder.

# 10. Where everything lives

| File (in the GitHub repo) | What it is |
| --- | --- |
| business/PARTNER-PLAYBOOK.md | This plan, kept up to date |
| business/CLAUDE.md | Instructions for your Claude |
| marketing/GAMEPLAN.md | The go-to-market plan |
| marketing/handoff/README.md | Marketing brief: numbers, links, brand, rules |
| marketing/print/ | Ready-to-print posters, coupon cards, driver poster and the Mailchimp email |
| marketing/outreach/ | Contact lists and ready-to-post ads, posts and scripts |
| marketing/outreach/west-metro/ | West-metro driver leads and flyer spots (events, schools, HOAs, boards) |

## Key links

- Website and app: plowbird.app

- Driver sign-up: plowbird.app/drive

- Storm Pass: plowbird.app/storm-pass

- Driver application (share this): plowbird.app/apply

- Admin dashboard, waitlist and driver approvals: plowbird.app/admin

- Forecast: weather.gov/mpx